## 2019 Deliverables
2019 Deliverables | Contractor | Cost | Timing | Funders
Transit Demand Modeling Study | Metro | 50000 | February | TriMet: $xxxx
Points O&D (Business plan behind each stop) |  |  |  | City $xxxx
Ridership Demographics
Economic, Environmental & Social Impact Study--Triple Bottom Line | EcoNorthwest & FFF Admin | 80000 | March | City $xxxx
User & Non User Benefits |  |  |  | Grant $xxxx
Benefit Cost Analyst
Environmental Impact
Resilience Planning
Triple Bottom Line
Health, Equity
Passenger Ferry Service Case Studies | Friends of Frog Ferry | 30000 | April-July | City $xxxx
Regional Operational Models |  |  |  | Grant $xxxx
Similar Global Models
Operational Infrastructure Report | HMS Consulting & Flowing Solutions & FFF Admin | 200000 | April-July | City $xxxx
River Access |  |  |  | Grant $xxxx
Cap Cost
Insurance, Fuel, Equipment
Training, Regulations, Certifications
Barriers to Development
Funding Strategies--Staffing and Professional Services |  | 290000 | 2018 Jan-Dec | City $xxxx
Business Plan & Accounting & Grant writing | FFF & Kingfisher Writing |  |  | Grant $xxxx
Governance | Horenstein Law & Miller Nash
Office Expenses/Intern & Marketing (web, newsletter, events & presentations) | Cuprum Creative
Advocacy, Leadership & Staffing | Friends of Frog Ferry
Media Relations & Social Media | Coates Kokes & Sparkloft
Government Affairs | Summit Strategies and The Leo Group
Total 2019 |  | 650000
2020 Finance Plan--Staffing and Professional Services | Friends of Frog Ferry 501(c)(3) + TBD | 650000 |  | State of Oregon: $
Infrastructure Dev. Plans |  |  |  | City of Vancouver: $
Startup Costs
Frog Ferry Feasibility Study: Costs & Suppliers
Go - No Go - City of Portland issues RFP for Operations (2022-23 - Service Starts)
Staffing, studies, plan, advocacy, stakeholder building, gov't and community relations
Total 2019-2020 |  | $1.3 million
2017 & 2018 Delivered value of $400,000 pro bono in advocacy, research, & definition of project approach and operations.
2019: $200,000 pro bono committed for media relations, social media, graphic and web design | legal, accounting, lobbying and event staging.